## Task Master
Task ID | Task Title | Task Type | Status | Priority | Start Date | End Date | Estimated Hours | Actual Hours | Dependencies | Remarks
T001 | Fix login API issue | Bug | Completed | High | 2026-03-31 | 2026-04-06 | 5 | 8 | No Dependencies | Stage Released
T002 | New Features- boiii | Feature222 | Testing | High | 2025-12-12 | 2026-04-07 | 20 | 31 | Moved to Staging env | Needs clarification of testing
T007 | Email Notification System | Feature | Testing | Medium | 2026-04-07 | 2026-04-08 | 30 | 12 | Database schema finalized | Backend API developed, now under testing
T008 | Mobile App Push Notifications | Feature | In Progress | High | 2026-04-07 |  | 40 | 4 | Firebase setup pending | Push notification module under development
Formulas:
Start Date = IFERROR(__xludf.DUMMYFUNCTION("ARRAYFORMULA(IF([Task ID]:A805="""", """", BYROW([Task ID]:A805, LAMBDA(task, IFERROR(MIN(FILTER('Daily Log'!A:A, 'Daily Log'!B:B=task)), """")))))"),46112.0)

## Daily Log
Date | Task ID | Task Type | Work Description | Hours Spent | Status Update | Remarks | Week | Month | Year
2026-03-31 | T001 | Bug | Fixed timeout issue and tested | 3 | In Progress |  | 14 | 3 | 2026
2026-04-05 | T001 | Bug | Fixed timeout issue and tested | 3 | Dev Completed |  | 14 | 4 | 2026
2026-04-06 | T001 | Bug | Fixed timeout issue and tested | 1 | Completed | Stage Released | 15 | 4 | 2026
2026-04-06 | T001 | Bug | Fixed timeout issue and tested | 1 | Completed | Stage Released | 15 | 4 | 2026
2025-12-12 | T002 | Feature | Started the work | 3 | In Progress | Pending with Data | 50 | 12 | 2025
2026-04-06 | T002 | Feature | Completed the work | 7 | Completed | Needs clarification | 15 | 4 | 2026
2026-04-06 | T002 | Feature | Completed the work | 7 | Completed | Needs clarification | 15 | 4 | 2026
2026-04-06 | T002 | Feature | Completed the work | 7 | Completed | Needs clarification | 15 | 4 | 2026
2026-04-06 | T002 | Feature222 | Completed the work | 7 | Completed | Needs clarification of testing | 15 | 4 | 2026
2026-04-07 | T007 | Feature | Set up email templates and SMTP configuration | 5 | In Progress | Backend API being developed | 15 | 4 | 2026
2026-04-07 | T008 | Feature | Configured Firebase project and initial push API | 4 | In Progress | Push notification module under development | 15 | 4 | 2026
2026-04-07 | T007 | Feature | Completed backend API and email template integration | 7 | Testing | Backend API developed, now under testing | 15 | 4 | 2026
Formulas:
Week = IF([Date]:A814="", "", WEEKNUM([Date]:A814, 2))

## Dashboard
Total Tasks | 1
Completed Tasks | 0
In Progress Tasks | 0
Blocked Tasks | 0
Total Hours | 3
Total Bugs Worked | 1
Total Features Worked | 0
Total Engineered | 0
Total Devops Task | 0
Total Bugs Completed | 0
Total Features Completed | 0
Total Engineered Completed | 0
Total Hours worked on Bug | 8
Total Hours worked on Features | 0
Productivity Score | 0